## Work Items
Item | Time estimate (min) | Time Spent (min) | Complete? | Notes
Read & Process project description | 30 | 40 | Yes
Initial Task diagram | 45 | 45 | Yes
Initial project description writeup | 30 | 60 | Yes
Initial unit testing plan | 60 | 45 | No | About 1/5 the way through. Yikes. Hoping this will go faster when I'm well rested.

## Risk Analysis
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Includes being a nightmare | 40 | 13 | 520 | 2021-10-29
Simplicity Studio Failure | 5 | 8 | 40 | 2021-10-29
0
0
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100