## Work Items
Item | Time estimate (min) | Time Spent (min) | Complete? | Notes | TOTAL EST TIME REQUIRED: | 1245
Read & Process project description | 30 | 40 | Yes |  | COMPLETED: | 555
Initial Task diagram | 45 | 45 | Yes |  | PERCENT COMPLETION EST: | 44.58%
Initial project description writeup | 30 | 60 | Yes |  | PERCENT TASK COMPL. EST: | 38.46%
Initial unit testing plan | 60 | 105 | Yes |  | PERCENT OF ESTIMATED TIME USED | 98.05%
Setup global task variables | 45 | 35 | Yes
Setup initial empty task code | 15 | 12 | Yes
Create initial task function prototypes | 60 | 60 | Yes
Create initial unit tests | 90 | 110 | Yes
Create Thrust Data structure | 15 | 9 | Yes
Create Thrust Input Task | 45 | 30 | Yes
Create Direction data structure | 15 | 7 | Yes
Create direction input task | 45 | 15 | Yes
Create craft position data structure | 15 | 5 | Yes
Create game settings struct | 15 | 15 | Yes
Create LCD Display Task | 90 |  | No
Create LED control data structure | 30 | 15 | Yes
Create LED0 control clock timers | 30 |  | No
Create LED1 control clock timers | 30 |  | No
Create LED0 control and on/off tasks | 60 |  | No
Create LED1 control and on/off tasks | 60 |  | No
Create Physics Task | 240 |  | No
Debug any final problems with unit tests. | 60 |  | No
Setup ITC methods | 120 |  | No
Create initial functional testing plan | 60 | 40 | Yes
Run functional testing plan | 30 |  | No

## Risk Analysis
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Capstone emergency takes all of my time for a week | 13 | 70 | 910 | 2021-11-11
Includes being a nightmare | 40 | 13 | 520 | 2021-10-29 |  | O | Once I have enough built out for my project to build at all, I'll be testing my includes to ensure that
Simplicity Studio Failure | 5 | 8 | 40 | 2021-10-29 |  | A | If it happens, I'll reinstall Simplicity. It'll suck but I'll live.
0
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100