## Work Items
Item | Time estimate (min) | Time Spent (min) | Complete? | Notes | TOTAL EST TIME REQUIRED: | 1305
Read & Process project description | 30 | 40 | Yes |  | COMPLETED: | 855
Initial Task diagram | 45 | 45 | Yes |  | PERCENT COMPLETION EST: | 65.52%
Initial project description writeup | 30 | 60 | Yes |  | PERCENT TASK COMPL. EST: | 60.98%
Initial unit testing plan | 60 | 105 | Yes |  | PERCENT OF ESTIMATED TIME USED | 91.58%
Setup global task variables | 45 | 35 | Yes
Setup initial empty task code | 15 | 12 | Yes
Create initial task function prototypes | 60 | 60 | Yes
Create initial unit tests | 90 | 110 | Yes
Create Thrust Data structure | 15 | 9 | Yes
Create Thrust Input Task | 45 | 30 | Yes
Create Direction data structure | 15 | 7 | Yes
Create direction input task | 45 | 15 | Yes
Create craft position data structure | 15 | 5 | Yes
Create game settings struct | 15 | 15 | Yes
Create LCD Display Task | 90 |  | No
Create LED control data structure | 30 | 15 | Yes
Create LED control functions | 15 | 15 | Yes
Create LED0 control clock timers | 30 | 20 | Yes
Create LED1 control clock timers | 30 | 5 | Yes
Create LED control tasks | 60 |  | No
Create LED on/off tasks | 60 | 20 | Yes
Define game settings | 45 | 35 | Yes
Create Physics functions | 120 | 140 | Yes
Create Physics Task | 120 |  | No
Debug any final problems with unit tests. | 60 |  | No
Setup ITC methods | 120 |  | No
Create initial functional testing plan | 60 | 40 | Yes
Run functional testing plan | 30 |  | No

## Risk Analysis
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Capstone emergency takes all of my time for a week | 13 | 70 | 910 | 2021-11-11
Includes being a nightmare | 40 | 13 | 520 | 2021-10-29 |  | O | Once I have enough built out for my project to build at all, I'll be testing my includes to ensure that
Simplicity Studio Failure | 5 | 8 | 40 | 2021-10-29 |  | A | If it happens, I'll reinstall Simplicity. It'll suck but I'll live.
0
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values | Direction in Begrees (data) | Direction in Degrees | Sine output | Sine Approximation | Sine Approx Multiplier | Cos Output | Cos Approximation | Cos Approx Multiplier
1 | 0 | 0 | 0 |  |  | 1
2 | 8 | 11.25 | 0.19509 | 0.19531 | 200 | 0.98079 | 0.98047 | 1004
3 | 16 | 22.5 | 0.38268 | 0.38281 | 392 | 0.92388 | 0.92383 | 946
5 | 24 | 33.75 | 0.55557 | 0.55566 | 569 | 0.83147 | 0.83105 | 851
8 | 32 | 45 | 0.70711 | 0.70703 | 724 | 0.70711 | 0.70703 | 724
13 | 40 | 56.25 | 0.83147 | 0.83105 | 851 | 0.55557 | 0.55566 | 569
20 | 48 | 67.5 | 0.92388 | 0.92383 | 946 | 0.38268 | 0.38281 | 392
40 | 56 | 78.75 | 0.98079 | 0.98047 | 1004 | 0.19509 | 0.19531 | 200
70 | 64 | 90 | 1 | 1 | 1024 | 0 | 0 | 0
100 | 72 | 101.25 | 0.98079 | 0.98047 | 1004 | -0.19509 | -0.19531 | -200
| 80 | 112.5 | 0.92388 | 0.92383 | 946 | -0.38268 | -0.38281 | -392
| 88 | 123.75 | 0.83147 | 0.83105 | 851 | -0.55557 | -0.55566 | -569
| 96 | 135 | 0.70711 | 0.70703 | 724 | -0.70711 | -0.70703 | -724
| 104 | 146.25 | 0.55557 | 0.55566 | 569 | -0.83147 | -0.83105 | -851
| 112 | 157.5 | 0.38268 | 0.38281 | 392 | -0.92388 | -0.92383 | -946
| 120 | 168.75 | 0.19509 | 0.19531 | 200 | -0.98079 | -0.98047 | -1004
| 128 | 180 | 0 | 0 | 0 | -1 | -1 | -1024
| 136 | 191.25 | -0.19509 | -0.19531 | -200 | -0.98079 | -0.98047 | -1004
| 144 | 202.5 | -0.38268 | -0.38281 | -392 | -0.92388 | -0.92383 | -946
| 152 | 213.75 | -0.55557 | -0.55566 | -569 | -0.83147 | -0.83105 | -851
| 160 | 225 | -0.70711 | -0.70703 | -724 | -0.70711 | -0.70703 | -724
| 168 | 236.25 | -0.83147 | -0.83105 | -851 | -0.55557 | -0.55566 | -569
| 176 | 247.5 | -0.92388 | -0.92383 | -946 | -0.38268 | -0.38281 | -392
| 184 | 258.75 | -0.98079 | -0.98047 | -1004 | -0.19509 | -0.19531 | -200
| 192 | 270 | -1 | -1 | -1024 | 0 | 0 | 0
| 200 | 281.25 | -0.98079 | -0.98047 | -1004 | 0.19509 | 0.19531 | 200
| 208 | 292.5 | -0.92388 | -0.92383 | -946 | 0.38268 | 0.38281 | 392
| 216 | 303.75 | -0.83147 | -0.83105 | -851 | 0.55557 | 0.55566 | 569
| 224 | 315 | -0.70711 | -0.70703 | -724 | 0.70711 | 0.70703 | 724
| 232 | 326.25 | -0.55557 | -0.55566 | -569 | 0.83147 | 0.83105 | 851
| 240 | 337.5 | -0.38268 | -0.38281 | -392 | 0.92388 | 0.92383 | 946
| 248 | 348.75 | -0.19509 | -0.19531 | -200 | 0.98079 | 0.98047 | 1004